## Slide 1
Week 11 – Tutorial No. 10
PRINCE2
6th – 9th October 2020
Tutor: <insert name here>
IFB295 – IT Project Management
Notes: 1
1
1

## Slide 2
Recap of Week 10 Tutorial
Product Breakdown Structure
Work Breakdown Structure
Questions / Queries regarding Assessment 2
Group Activity

## Slide 3
Today’s Learning Outcome
Gantt Chart
Project Resource Management Technique
Questions / Queries regarding Assessment 3
Team Activity – Mika Music School

## Slide 4
Scheduling with Gantt Charts
Establish a timeline. MS Project
Left hand side is the tabular form of the WBS.
Right hand side is the Gantt Chart of the Project.
(Critical Path (CP) tasks in red, Non-critical path tasks in blue).
4

## Slide 5
Resources and Constraints
Example:
Resource
Usage
Table
Resource
Chart
5

## Slide 6
Resource Levelling
Benefits
More constant, uniform and consistent use of resources:
  requires less management.
  enables just-in-time inventory policy for expensive resources.
  results in fewer problems for project personnel and accounting department.
  improves morale.
6

## Slide 7
Example: Project with 6 tasks (U to Z)
Use a network diagram to determine the Critical Path
ID | Task | Pred. | Expected Time (ET) | ES | EF | LS | LF | Slack | Resource (R1)
1 | Z |  | 4 | 0 | 4 | 0 | 4 | 0 | 6
2 | Y | Z | 1 | 4 | 5 | 4 | 5 | 0 | 2
3 | X | Z | 3 | 4 | 7 | 8 | 11 | 4 | 2
4 | W | Y | 4 | 5 | 9 | 5 | 9 | 0 | 7
5 | V | W | 2 | 9 | 11 | 9 | 11 | 0 | 3
6 | U | V, X | 1 | 11 | 12 | 11 | 12 | 0 | 6
Week 10 Lecture covered Critical Path technique.
For this example, the Critical Path: Z, Y, W, V, U
This example is used to demonstrate resource levelling.
7

## Slide 8
Example: Project with 6 tasks (U to Z)
Create a Resource loading chart
Initially schedule all tasks to commence at early start (ES) time.
Resource (R1) loading chart shows peak of 9 on days 6 and 7.
Questions: Is this an issue?
If the resource R1 was Business Analysts (BA’s)?
If you only had 7 BA’s what then?
ID | Task | Expected Time (ET) | ES | LF | Slack | Resource (R1)
1 | Z | 4 | 0 | 4 | 0 | 6
2 | Y | 1 | 4 | 5 | 0 | 2
3 | X | 3 | 4 | 11 | 4 | 2
4 | W | 4 | 5 | 9 | 0 | 7
5 | V | 2 | 9 | 11 | 0 | 3
6 | U | 1 | 11 | 12 | 0 | 6
8

## Slide 9
Resource Levelling
Resource levelling heuristic.
Identify the task to alter in order to level resources. Prioritised rules, start with the task with:
Smallest amount of slack.
Smallest duration.
Lowest ID number - First Come First Served (FCFS).
Greatest number of successor tasks.
Requiring the most resources.
Heuristic - practical method to solve a problem. It is not guaranteed to be
optimal or perfect, but sufficient for the immediate goals.
9

## Slide 10
Example: Project with 6 tasks (U to Z)
Create a Resource load chart
Using Rule1, Task X has Slack, rearrange activity within the slack to create a more level profile. Splitting Task X creates a more level resource profile.
Resource (R1) loading chart now shows peak load of 7 resources
on days 5 to 9.
Question: is this an improvement?
ID | Task | Expected Time (ET) | ES | LF | Slack | Resource (R1)
1 | Z | 4 | 0 | 4 | 0 | 6
2 | Y | 1 | 4 | 5 | 0 | 2
3 | X | 3 | 4 | 11 | 4 | 2
4 | W | 4 | 5 | 9 | 0 | 7
5 | V | 2 | 9 | 11 | 0 | 3
6 | U | 1 | 11 | 12 | 0 | 6
10

## Slide 11
Assessment 3 - Queries
Any Questions?
If not proceed to Team Activity (next slide)

## Slide 12
Mika Music School Case Study
Team Activity
Based on your project plan and the IT solution being developed for Mika Music School,
Construct a Gantt Chart
Construct a Resource Load Chart

## Slide 13
In your teams:
Team Activity – Mika Music School
Use the Mika Music School case study to complete these exercises:
Revise your WBS (estimate costs, duration, resources) from last week’s tutorial
Use your WBS above to develop a Gantt Chart
Develop a Resource Loading and Levelling Chart
Discuss your work with your Tutor / also upload on Trello
Note: Key learning for this week’s tutorial are likely to be in the final exams
Notes: 13
13

## Slide 14
Example of WBS from Last Week Tutorial
Revise what you did last week. Then create a Gantt Chart

## Slide 15
Homework (To be completed)
1. Read
Prince2 Guide – Section on Project Governance: (http://prince2.wiki/Processes)
Assessment 3 – Submissions.
Presentation Slides - Due on Friday, 9th October 2020 @ 11:59pm
Team’s Present in their Week 12 tutorials (12th – 16th October 2020)
Reading Material (DSDM Guide & Prince2 Guide) – are on blackboard

## Slide 16
Close / Wrap Up
I look forward to your contributions next week
Thank you for your participation.
Notes: 16
16
16
16